## Sheet1
Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Monday | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22
Tuesday | 2020-09-01 | 2020-09-08 | 2020-09-15 | 2020-09-22 | 2020-09-29 | 2020-10-06 | 2020-10-13 | 2020-10-20 | 2020-10-27 | 2020-11-03 | 2020-11-10 | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2020-12-15 | 2020-12-22 | 2020-12-29 | 2021-01-05 | 2021-01-12 | 2021-01-19 | 2021-01-26 | 2021-02-02 | 2021-02-09 | 2021-02-16 | 2021-02-23
Wednesday | 2020-09-02 | 2020-09-09 | 2020-09-16 | 2020-09-23 | 2020-09-30 | 2020-10-07 | 2020-10-14 | 2020-10-21 | 2020-10-28 | 2020-11-04 | 2020-11-11 | 2020-11-18 | 2020-11-25 | 2020-12-02 | 2020-12-09 | 2020-12-16 | 2020-12-23 | 2020-12-30 | 2021-01-06 | 2021-01-13 | 2021-01-20 | 2021-01-27 | 2021-02-03 | 2021-02-10 | 2021-02-17 | 2021-02-24
Thursday | 2020-09-03 | 2020-09-10 | 2020-09-17 | 2020-09-24 | 2020-10-01 | 2020-10-08 | 2020-10-15 | 2020-10-22 | 2020-10-29 | 2020-11-05 | 2020-11-12 | 2020-11-19 | 2020-11-26 | 2020-12-03 | 2020-12-10 | 2020-12-17 | 2020-12-24 | 2020-12-31 | 2021-01-07 | 2021-01-14 | 2021-01-21 | 2021-01-28 | 2021-02-04 | 2021-02-11 | 2021-02-18 | 2021-02-25
Friday | 2020-09-04 | 2020-09-11 | 2020-09-18 | 2020-09-25 | 2020-10-02 | 2020-10-09 | 2020-10-16 | 2020-10-23 | 2020-10-30 | 2020-11-06 | 2020-11-13 | 2020-11-20 | 2020-11-27 | 2020-12-04 | 2020-12-11 | 2020-12-18 | 2020-12-25 | 2021-01-01 | 2021-01-08 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-05 | 2021-02-12 | 2021-02-19 | 2021-02-26
Weekly events | 2020-09-04: Orientation and preperations; 2020-09-11: Kickoff + start phase 1; 2020-11-06: 50% presentation; 2021-01-22: Complete assignment; 2021-01-29: Finish report
Phase progress | 2020-09-11: Phase 0; 2020-10-09: Phase 1; 2020-11-20: Phase 2; 2020-12-25: Extension week; 2021-01-01: Extension week; 2021-01-08: Extension week; 2021-01-15: Phase 3 - Extension week; 2021-02-05: Deadline
Weekly progress | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | In progress | Not done | Not done
Month | Aug/Sep | Sep | Sep | Sep | Sep/Oct | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Nov/Dec | Dec | Dec | Dec | Dec/Jan | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb
Workday
Not yet occured
No workday
Vacationday